## Project Timeline
Project Name: | VM EXPLOIT
Project Team Members: | Emma Feaga, Johnathan Hudachek, Theresa Lee
Due Time: | Start of class | End of Day
Project Milestone | Due | Details | Notes from Standup with Instructor
Proposal + Team Contract | 2021-06-26 | Propose your idea to two (2) separate instructors for approval
Proof of Concept | 2021-06-29 | Can this idea turn into a reality? What do you need to do to prove it? The point is to identify any technical issues you may have. Determine if your project can be done.
Minimum Viable Product | 2021-07-01 | You have achieved the absolute minimum as far as necessary features show in PoC phase. This may look like you have solved your problem/challenge for at least one case.
Complete Project | 2021-07-10 | Iron out the kinks, receive feedback from peers and instructors, iterate over the MVP
First Draft Script and Demo | 2021-07-13 | Script must be complete and demo'd to instructors
Recording | 2021-07-15 | Zoom or Camtasia recording complete
Complete Presentation | 2021-07-15 | Any final touches / editing - Share with friends, family, and social media.
Present Project | Satuday 7/17 | Present Projects during graduation/friends & family

## Project Proposal
Project Name: | VM EXPLOIT
Project Team Members: | Emma Feaga, Johnathan Hudachek, Theresa Lee
Specifics For Your Project
Overview | Choose a recent exploit and setup a VM that is vulnerable to the exploit. Write a tutorial about how to execute the exploit, and/or how to defend against it.
Proof of Concept (PoC) | 1. What our project is trying to achieve:
Our VM Exploit project will use exploit 50053 from Exploitdb for Online Library Management System 1.0 - 'Search' SQL Injection. We will create a VM that hosts a website on which this exploit will work. We will create a tutorial for how to execute the exploit to access the information within the VM.
2. How we will get the project done:
a. Create the initial VM. b. Load all necessary software/files to the VM. c. Create the website that will run on the VM. d. Beta test the operation of the VM, the website, and any files/software. e. Run the exploit against the VM ... until we get everything to work correctly. f. Document all steps for running the exploit, including screenshots of each step. g. Create the tutorial. h. Beta test the tutorial. If it needs changes/corrections, make those. i. Re-test the tutorial. If it needs changes/corrections, make those. j. Once the tutorial, if followed correctly, runs the exploit correctly, then publish the tutorial and the VM.
3. What specific tasks/goals will be there for us to consider the project complete:
a. The VM is created with all necessary files operating. b. We are able to run the exploit on the VM as intended. c. The tutorial, if followed correctly, works as intended. g. The tutorial and the VM are published on the github.
Minimum Viable Project (MVP) | a. The necessary software/files must be suitable to the VM. B. The website created must be able to run and work efficiently. C. The exploit must be able to effectively attack the VM. D. The tutorial must be executable by anyone with at least a fundamental level of cybersecurity exploit experience and knowledge.
Complete Project
Stretch Goals | a. Demonstrate how to defend agains the SQL injection. B. Add an additional vulnerability/flag to find within the VM.

## External Resources
Resource | Link | Notes:
Github | https://github.com/EmmaFeaga/Exploit-Tutorial | Repository for our code
Exploitdb | https://www.exploit-db.com/exploits/24044 | This is the exploit we are going to use to attack the VM and/or defend the VM