## Project Timeline
Project Name:
Project Team Members:
Due Time: | Start of class | End of Day
Project Milestone | Due | Details | Notes from Standup with Instructor
Proposal + Team Contract | 2021-06-26 | Propose your idea to two (2) separate instructors for approval
Proof of Concept | 2021-06-29 | Can this idea turn into a reality? What do you need to do to prove it? The point is to identify any technical issues you may have. Determine if your project can be done.
Minimum Viable Product | 2021-07-01 | You have achieved the absolute minimum as far as necessary features show in PoC phase. This may look like you have solved your problem/challenge for at least one case.
Complete Project | 2021-07-10 | Iron out the kinks, receive feedback from peers and instructors, iterate over the MVP
First Draft Script and Demo | 2021-07-13 | Script must be complete and demo'd to instructors
Recording | 2021-07-15 | Zoom or Camtasia recording complete
Complete Presentation | 2021-07-15 | Any final touches / editing - Share with friends, family, and social media.
Present Project | Satuday 7/17 | Present Projects during graduation/friends & family

## Project Proposal
Project Name:
Project Team Members:
Specifics For Your Project
Overview
PoC
MVP
Complete Project
Stretch Goals

## External Resources
| Link | Notes:
Ex. Github |  | Ex. Repo for our code
Working Doc |  | ex. This is the doc we are sharing / brainstroming on